## ProjectOverview
Project Name | Real-Time Performance Dashboard Feature
Project Start | 2025-01-15
Project Manager Agent | engineer-memes-project-manager
Total Agents | 6
MCP Servers | excel-vba, svgmaker-mcp, opencv
Complexity Score | 9.2/10
Estimated Duration | 5-7 days
Success Criteria | Comprehensive analytics dashboard with real-time metrics
Quality Gate Standard | Professional engineering grade with 95%+ agent collaboration efficiency

## AgentAssignments
Agent | Primary Responsibilities | Dashboard Components | MCP Integration | Estimated Hours | Dependencies
Frontend Dev Agent | React dashboard components, real-time UI, responsive design | Performance metrics display, real-time charts, mobile-optimized layout | svgmaker-mcp for graphics, opencv for visual validation | 24 | Backend API endpoints
Backend Dev Agent | WebSocket analytics endpoints, performance data collection | Real-time data streaming, analytics aggregation, API design | excel-vba for performance tracking and analytics storage | 20 | Frontend component specs
QA Engineer Agent | Comprehensive testing, load validation, quality assurance | Test automation, performance benchmarking, quality validation | excel-vba for test metrics, opencv for automated UI testing | 18 | All agent deliverables
Content Manager Agent | Performance-related content and visual optimization | Dashboard content strategy, visual hierarchy, engagement metrics | svgmaker-mcp for dashboard graphics, excel-vba for content analytics | 12 | Frontend layout decisions
DevOps Agent | Production deployment, monitoring setup, infrastructure management | Deployment pipeline, monitoring configuration, performance alerts | excel-vba for deployment metrics and operational tracking | 16 | Backend and frontend completion
Project Manager Agent | Coordination, quality gates, progress tracking | Project oversight, agent coordination, milestone validation | excel-vba for comprehensive project tracking and reporting | 22 | All agent coordination

## DependencyMatrix
Phase | Agent | Milestone | Dependencies | Deliverables | Timeline
Phase 1: Planning | Project Manager | Requirements Analysis | None | Technical specifications, agent task briefs | Day 1
Phase 1: Planning | Backend Dev | API Design | Requirements Analysis | WebSocket endpoints, data models | Day 1-2
Phase 1: Planning | Frontend Dev | Component Architecture | API Design | React component specifications | Day 2
Phase 2: Development | Backend Dev | Analytics Implementation | API Design complete | Performance data collection, real-time streaming | Day 2-3
Phase 2: Development | Frontend Dev | Dashboard UI | Analytics Implementation | Performance metrics display, real-time charts | Day 3-4
Phase 2: Development | Content Manager | Visual Optimization | Dashboard UI progress | Graphics, content strategy, visual hierarchy | Day 3-4
Phase 3: Integration | QA Engineer | Testing Framework | All development 60% complete | Test suites, validation procedures | Day 4-5
Phase 3: Integration | All Agents | Cross-Agent Integration | Individual components complete | Integrated dashboard functionality | Day 5
Phase 4: Validation | QA Engineer | Quality Validation | Integration complete | Performance benchmarks, quality report | Day 5-6
Phase 5: Deployment | DevOps | Production Deployment | Quality Validation passed | Live dashboard, monitoring setup | Day 6-7
Phase 5: Deployment | Project Manager | Project Completion | All phases complete | Final coordination report, success metrics | Day 7

## MCPIntegrationStrategy
MCP Server | Primary Agent | Secondary Agents | Applications | Expected Benefits
excel-vba | Project Manager Agent | Backend Dev, QA Engineer, DevOps | Project metrics tracking, performance analytics, coordination reporting | Comprehensive project tracking with 95%+ data accuracy
svgmaker-mcp | Frontend Dev Agent | Content Manager Agent | Dashboard graphics, performance visualization, UI elements | Professional visual design with corporate-grade aesthetics
opencv | QA Engineer Agent | Frontend Dev Agent | Automated UI testing, visual regression detection, performance validation | 90%+ automated quality validation with visual consistency
excel-vba (Analytics) | Backend Dev Agent | All Agents | Performance data logging, user analytics, system metrics | Real-time analytics with comprehensive historical tracking
svgmaker-mcp (Content) | Content Manager Agent | Frontend Dev Agent | Performance-related graphics, engagement visualization | Enhanced user engagement through professional visual content
excel-vba (Operations) | DevOps Agent | QA Engineer Agent | Deployment tracking, operational metrics, infrastructure monitoring | Operational excellence with 99.9% uptime monitoring

## QualityGates
Quality Gate | Success Criteria | Validation Method | Responsible Agent | Dependencies | Target Score
Code Quality | TypeScript strict compliance, ESLint passing, 90%+ test coverage | Automated testing, code analysis | QA Engineer Agent | Frontend/Backend Dev completion | 95%
Performance Standards | Sub-200ms API response, real-time WebSocket <50ms latency | Load testing, performance benchmarking | QA Engineer Agent | Backend implementation | 98%
UI/UX Excellence | Mobile-responsive, accessibility compliant, professional design | Visual regression testing, accessibility audit | Frontend Dev + QA Engineer | Frontend completion | 92%
Real-time Functionality | Live dashboard updates, accurate metrics display | End-to-end testing, integration validation | All Technical Agents | Full integration | 96%
Content Appropriateness | Professional corporate standards, executive-ready presentation | Content validation, professional review | Content Manager + QA Engineer | Dashboard completion | 98%
Deployment Excellence | Zero-downtime deployment, monitoring configured, rollback ready | Deployment testing, operational validation | DevOps + QA Engineer | All development complete | 99%
Agent Coordination | 95%+ task completion rate, cross-agent dependency resolution | TodoWrite tracking, milestone validation | Project Manager Agent | All agent participation | 97%
MCP Integration | Maximum efficiency through server utilization, data accuracy | Integration testing, performance validation | All Agents | MCP server availability | 94%

## SuccessMetrics
Metric Category | Specific Metric | Target Value | Measurement Method | Tracking Agent
Agent Performance | Autonomous Operation Percentage | 80%+ | TodoWrite completion tracking | Project Manager Agent
Agent Performance | Cross-Agent Coordination Efficiency | 95%+ | Dependency resolution time | Project Manager Agent
Agent Performance | MCP Server Utilization Rate | 90%+ | Integration effectiveness measurement | All Agents
Technical Excellence | Dashboard Load Time | <2 seconds | Performance testing | QA Engineer Agent
Technical Excellence | Real-time Update Latency | <100ms | WebSocket performance testing | Backend Dev Agent
Technical Excellence | Mobile Responsiveness Score | 95%+ | Cross-device testing | Frontend Dev Agent
User Experience | Professional Appropriateness Score | 98%+ | Content validation | Content Manager Agent
User Experience | Dashboard Usability Score | 92%+ | User interaction testing | Frontend Dev + QA Engineer
Operational Excellence | Deployment Success Rate | 99%+ | Deployment tracking | DevOps Agent
Operational Excellence | System Uptime | 99.9%+ | Monitoring systems | DevOps Agent
Business Impact | Corporate Entertainment Value | 85%+ | Engagement metrics | Content Manager Agent
Business Impact | Team Productivity Enhancement | 15%+ | Usage analytics | Backend Dev Agent